## All Features
[5 empty] | Completed Features | Person
Area | Highlevel | Lowlevel | Priority | Difficulty (*/10)
UI | [6 empty] | Person | Number of tasks | Incomplete | Complete | Proportion Complete
| Menu | HTML+CSS | Medium | 3 | No | Casie | Casie | 20 | 18 | 2 | 10%
|  | Links | Medium | 1 | No | Casie | Kim | 26 | 23 | 3 | 11.54%
|  | Send Data to Backend (Logout) | High | 3 | No | Casie | Shinjini | 36 | 2 | 33 | 91.67%
| Search through old connections | HTML+CSS | Low | 1 | No |  | Total | 82 | 43 | 38 | 46.34%
UI | Search through old connections | Algorithm | Low | 5 | Yes | Shinjini
| Sort journal entries | HTML+CSS | Low | 1 | No | Casie
UI | Sort journal entries | Algorithm | Low | 3 | Yes | Shinjini
UI | Calendar | HTML+CSS | High | 2 | Yes | Shinjini
UI | Calendar | Responsiveness | High | 3 | Yes | Shinjini
UI | Calendar | Select Range | Low |  | Yes | Shinjini
UI | Calendar | Use Data from Backend | High | 5 | Yes | Shinjini
UI | Calendar | Send Data to Backend | High | 5 | Yes | Shinjini
| Dashboard listing | HTML+CSS | High | 4 | No | Casie
UI | Dashboard listing | Use Data from Backend | High | 5 | Yes | Shinjini
UI | Dashboard listing | Send Data to Backend | High | 5 | Yes | Shinjini
| Journal listing | HTML+CSS | High | 4 | No | Casie
|  | Use Data from Backend | High | 5 | No | Casie
|  | Send Data to Backend | High | 5 | No | Casie
| Journal timeline | HTML+CSS | Low | 7 | No | Casie
UI | Journal timeline | Use Data from Backend | Low | 5 | Yes | Shinjini
| Signin Screen | HTML+CSS | High | 3 | Yes | Casie
UI | Signin Screen | Send Data to Backend | High | 2 | Yes | Shinjini
| Topics | UI for selecting and unselecting topics | Medium | 6 | No | Casie
|  | Send topic interest updates to Backend | High | 2 | No | Kim
| Account Settings | UI for unselecting disinterested_in and blocked users | Medium | 5 | No | Casie
|  | Use Data from Backend | Medium | 2 | No | Kim
|  | Send Data to Backend | Medium | 2 | No | Kim
| Admin interface | HTML+CSS | Medium | 2 | No | Kim
|  | UI for adding and removing topics | Medium | 2 | No | Kim
|  | Use Data from Backend | Medium | 2 | No | Kim
|  | Send data to backend | Medium | 2 | No | Kim
| Profile | HTML+CSS | Medium | 2 | No | Casie
|  | UI for adding and selecting location | Medium | 2 | No | Kim
|  | Send location updates to backend | Medium | 2 | Yes | Kim
|  | UI for selecting and unselecting topics | Medium | 6 | No | Kim
|  | Send topic interest updates to Backend | High | 2 | No | Kim
Authentication
Authentication | Signup | Route | High | 8 | Yes | Shinjini
Authentication | Signup | Database | High | 8 | Yes | Shinjini
Authentication | Login | Route | High | 8 | Yes | Shinjini
Authentication | Login | Database | High | 8 | Yes | Shinjini
Authentication | Logout | Route | High | 8 | Yes | Shinjini
Authentication | Logout | Database | High | 8 | Yes | Shinjini
Authentication | Inputs | Check inputs are sanitized | High | 3 | Yes? | Shinjini
Profile (db)
| Storing | Location | High | 3 | Yes | Kim
|  | Topics | High | 2 | No | Kim
Profile (db) | Storing | Preferences | High | 3 | Yes | Shinjini
| Editing | Location | Low | 2 | Yes | Kim
|  | Topics | Low | 2 | No | Kim
Profile (db) | Editing | Preferences | Low | 2 | Yes | Shinjini
Account Settings (db)
| Store and make editable | Password | Low | 2 | No | Kim
|  | Send password reset email | Very Low |  | No | Kim
|  | Compose password reset email | Very Low |  | No | Kim?
| Store and make editable | Email | Low | 2 | No | Kim
| Store and make editable (can delete users from) | Blocklist | Low | 3 | No | Casie
| Store and make editable (can delete users from) | Disinterest list | Low | 3 | No | Casie
Topics (db)
| Update topic list admin interface | UI |  |  | No | Kim
|  | Send updated topic list to backend |  |  | No | Kim
| List of topics | Need to choose a set of topics for users to select from | Low-Medium | ? | No | Kim
Suggestion
Suggestion | Suggestion algorithm | Time | High | 8 | Yes | Shinjini
Suggestion | Suggestion algorithm | Location | High | 7 | Yes | Shinjini
Suggestion | Suggestion algorithm | Location, more advanced | Low |  | Yes | Shinjini
Suggestion | Suggestion algorithm | Preferences (topics) | Medium | 3 | No | Shinjini
Suggestion | Suggestion algorithm | Use information from blocklist + disinterest list | Low | 3 | Yes | Shinjini
Suggestion | Suggestion algorithm | Location: match area around given zipcode | Low | 8 | Yes | Shinjini
Connections (db)
Connections (db) | Algorithm | Making sure interest used is still relevant (the availabilities still overlap) at the time of running the algorithm | High | 8 | Yes | Shinjini
Connections (db) | Algorithm | Make sure only to use the next week for checking | High |  | Yes | Shinjini
| Algorithm | Smarter: choose connection other than just randomly | Medium |  | No | Shinjini
| Communication | Routing user-to-user emails via the app | Medium | 7 | No | Kim
|  | Compose default email with html and stuff | Medium |  | No | Casie?
|  | Make sure user emails stay hidden from other users in emails | Medium |  | No | Kim
| Blocked users | Send user block to backend | Low | 2 | No | Casie
Connections (db) | Closing → new connection | Sending Data to Backend | High | 4 | Yes | Shinjini
Connections (db) | Closing → new connection | Using Data from Backend | High | 4 | Yes | Shinjini
Journal
| Connection Record | Using Data from Backend | Medium-High | 2 | Yes | Casie
Journal | Notes | Making | Medium-High | 4 | Yes | Shinjini
Journal | Notes | Editing | Low | 6 | Yes | Shinjini
Journal | Notes | Sending Data to Backend | High | 3 | Yes | Shinjini
Journal | Notes | Using Data from Backend | High | 3 | Yes | Shinjini
| User Nicknames | Sending Data to Backend | Low | 2 | No | Casie
|  | Using Data from Backend | Low | 2 | No | Casie
| Add to disinterest list, block, report | Sending Data to Backend | Medium | 4 | No | Casie
Journal | Inputs (Notes) | Check inputs are sanitized | High | 3 | Yes | Shinjini
Admin Interface
| Routes | Create route for admin interface | Medium |  | No | Kim
|  | Make sure only admins can follow admin routes | Medium |  | No | Kim
| Security | Make sure only admin can access admin interface | Medium |  | No | Kim

## MVP Features
MVP
Area | Highlevel | Lowlevel | Priority | Difficulty (*/10) | Done?
UI
| Menu | Send Data to Backend (Logout) | High | 3 | No
| Calendar | HTML+CSS | Medium | 2 | Yes
|  | Responsiveness | Medium | 3 | Yes
|  | Send Data to Backend | High | 5 | Yes
|  | Use Data from Backend | High | 5 | Yes
| Dashboard listing | HTML+CSS | High | 4
|  | Use Data from Backend | High | 5 | Mostly
|  | Send Data to Backend | High | 5 | Mostly
| Journal listing | HTML+CSS | High | 4
|  | Use Data from Backend | High | 5 | Yes
|  | Send Data to Backend | High | 5 | Yes
| Signin Screen | HTML+CSS | High | 3 | Yes
|  | Send Data to Backend | High | 2 | Yes
Topics
|  | Send Data to Backend | Medium | 2
Authentication
| Signup | Route | High | 8 | Yes
|  | Database | High | 8 | Yes
| Login | Route | High | 8 | Yes
|  | Database | High | 8 | Yes
| Logout | Route | High | 8 | Yes
|  | Database | High | 8 | Yes
User info
| Storing | Location | High | 3 | Yes
|  | Topics | High | 2 | No
|  | Preferences | High | 3
Topics
| List of topics | Need to choose a set | Low-Medium | ? | No
Matching
| Matching algorithm | Time | High | 8 | Yes
|  | Location | High | 7 | Yes
Connection:
| Algorithm | Making sure interest used is still relevant (the availabilities still overlap) at the time of running the algorithm | High | 8 | Yes
| Closing → new connection | Sending Data to Backend | Medium | 4 | Yes
|  | Using Data from Backend | Medium | 4 | Yes
Journal
| Connection Record | Using Data from Backend | Medium-High | 2 | Yes

## Shinjini's Checklist
High Level Feature | Associated Task | Anticipated Time | Assigned Member | Completed? | Actual Time | Reviewed? | Review By | Comments
Calendar | HTML+CSS |  | Shinjini | Yes |  | Yes
| Responsiveness |  | Shinjini | Yes |  | Yes
3 hours
Signup | Route |  | Shinjini | Yes |  | Yes
| Database |  | Shinjini | Yes |  | Yes
Login | Route |  | Shinjini | Yes |  | Yes
| Database |  | Shinjini | Yes |  | Yes
Logout | Route |  | Shinjini | Yes |  | Yes
| Database |  | Shinjini | Yes |  | Yes
4 hours
Matching algorithm | Time |  | Shinjini | Yes |  | Yes
| Location |  | Shinjini | No
3/4 hours
Calendar | Send Data to Backend | 1 hour | Shinjini | Yes |  | Yes
| Use Data from Backend | 2/3 hours | Shinjini | Yes |  | Yes
5 hours total
Signin Screen | HTML+CSS | 1 hour | Shinjini | Yes |  | Yes
| Send Data to Backend | 1 hour | Shinjini | Yes |  | Yes
3.5 hours
Dashboard listing | Use Data from Backend | 2 hours | Shinjini | Yes |  | No
+ fixes in other parts of code
3 hours
Connection | Algorithm | 3 hours | Shinjini | Yes |  | No
Making sure interest used is still relevant (the availabilities still overlap) at the time of running the algorithm
Dashboard listing | Send Data to Backend | 2 hours | Shinjini | Yes |  | No
4 hours
Connection | Closing → new connection |  | Shinjini | Yes
| Sending Data to Backend |  | Shinjini | Yes
| Using Data from Backend |  | Shinjini | Yes
|  | 4 hours |  |  | 6 hours
| Storing previous connections | 2 hours | Shinjini | Yes | 1 hour
[9 empty] | Add to Do not match again list, block, report | Sending Data to Backend | Medium | 4